## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US1 | Setup Streamlit UI for dashboard | High | None | MASAPALLI CHIRANJEEVI | Completed
Sprint 1 | Sprint 1 | US2 | Database integration using SQLite | High | US1 | MASAPALLI CHIRANJEEVI | Completed
Sprint 1 | Sprint 1 | US3 | File upload support (TXT, CSV, Excel) | High | US1 | MASAPALLI CHIRANJEEVI | Completed
Sprint 1 | Sprint 1 | US4 | Text cleaning and preprocessing | High | US3 | MASAPALLI CHIRANJEEVI | Completed
Sprint 1 | Sprint 1 | US5 | Chunk processing for large datasets | High | US4 | MASAPALLI CHIRANJEEVI | Completed
Sprint 1 | Sprint 1 | US6 | Parallel processing implementation | High | US5 | MASAPALLI CHIRANJEEVI | Completed
Sprint 1 | Sprint 1 | US7 | Sentiment analysis using VADER | High | US4 | MASAPALLI CHIRANJEEVI | Completed
Sprint 1 | Sprint 1 | US8 | Dashboard charts and metrics | Medium | US6 | MASAPALLI CHIRANJEEVI | Completed
Sprint 1 | Sprint 1 | US9 | Search functionality | High | US2 | MASAPALLI CHIRANJEEVI | Completed
Sprint 1 | Sprint 1 | US10 | Export results to CSV | Medium | US2 | MASAPALLI CHIRANJEEVI | Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 290 | 30 | 30 | 30 | 30 | 30 | 20 | 20 | 20 | 20 | 20 | 10 | 10 | 10 | 10
SPRINT 1 BACKLOG
US1 | T1 | Project Setup | 09-02-2026 | 12-02-2026 | MASAPALLI CHIRANJEEVI | Setup Streamlit | Completed | 29 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1
US2 | T2 | Database Setup | 13-02-2026 | 16-02-2026 | MASAPALLI CHIRANJEEVI | SQLite | Completed | 29 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1
US3 | T3 | File Upload | 17-02-2026 | 21-02-2026 | MASAPALLI CHIRANJEEVI | Upload files | Completed | 29 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1
US4 | T4 | Data Cleaning | 22-02-2026 | 25-02-2026 | MASAPALLI CHIRANJEEVI | Clean text | Completed | 29 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1
US5 | T5 | Chunk Processing | 26-02-2026 | 03-03-2026 | MASAPALLI CHIRANJEEVI | Split data | Completed | 29 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1
US6 | T6 | Parallel Processing | 04-03-2026 | 09-03-2026 | MASAPALLI CHIRANJEEVI | Multi-core | Completed | 29 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1
US7 | T7 | Sentiment Analysis | 10-03-2026 | 15-03-2026 | MASAPALLI CHIRANJEEVI | VADER | Completed | 29 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1
US8 | T8 | Dashboard | 16-03-2026 | 20-03-2026 | MASAPALLI CHIRANJEEVI | Charts | Completed | 29 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1
US9 | T9 | Search | 21-03-2026 | 25-03-2026 | MASAPALLI CHIRANJEEVI | Keyword | Completed | 29 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1
US10 | T10 | Export | 26-03-2026 | 30-03-2026 | MASAPALLI CHIRANJEEVI | CSV | Completed | 29 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Environment setup issue | Installed Streamlit
Sprint 1 | Day 5 | File upload error | Fixed encoding
Sprint 1 | Day 10 | Crash large files | Chunk processing
Sprint 1 | Day 15 | Slow performance | Parallel added
Sprint 1 | Day 20 | Wrong sentiment | Logic fixed
Sprint 1 | Day 25 | Search issue | SQL fixed
Sprint 1 | Day 30 | UI slow | Optimized

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 09-02-2026 | 20-02-2026 | MASAPALLI CHIRANJEEVI | Follow coding | Avoid random | Continue planning | Checklist created
2 | Sprint 1 | 21-02-2026 | 10-03-2026 | MASAPALLI CHIRANJEEVI | Test large data | Avoid ignoring | Continue debug | System stable
3 | Sprint 1 | 11-03-2026 | 25-03-2026 | MASAPALLI CHIRANJEEVI | Optimize | Avoid loops | Continue testing | Speed improved
4 | Sprint 1 | 26-03-2026 | 30-03-2026 | MASAPALLI CHIRANJEEVI | Improve UI | Avoid incomplete | Continue refining | Project done